## Ark1
Team
Name | Alias | Field
Kristian | K | Project Manager
Nils | N | Copywriter/advisor
Gry | G | Digital marketer/photographer/researcher
Kyrill | Ky | Designer (UX/UI)
Frikk | F | Front-end Developer |  |  |  | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5
Terje | T | Back-end Developer/CTO
Owner | O | Owner of Lofthus product
[6 empty] | 2020-04-01 | 2020-04-02 | 2020-04-03 | 2020-04-04 | 2020-04-05 | 2020-04-06 | 2020-04-07 | 2020-04-08 | 2020-04-09 | 2020-04-10 | 2020-04-11 | 2020-04-12 | 2020-04-13 | 2020-04-14 | 2020-04-15 | 2020-04-16 | 2020-04-17 | 2020-04-18 | 2020-04-19 | 2020-04-20 | 2020-04-21 | 2020-04-22 | 2020-04-23 | 2020-04-24 | 2020-04-25 | 2020-04-26 | 2020-04-27 | 2020-04-28 | 2020-04-29 | 2020-04-30 | 2020-05-01 | 2020-05-02 | 2020-05-03 | 2020-05-04 | 2020-05-05
[6 empty] | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU
|  |  | Stage | Tasks | In charge (involved)
|  |  | 01. Planning | Going over business plan | Project Manager (K,O,N,G) | bar: 2020-04-01
|  |  |  | Redefining company goals | Project Manager (K,O,N,G) | bar: 2020-04-02
|  |  |  | Stakeholder meeting | Project Manager (K,O) | bar: 2020-04-01
|  |  |  | Accessing old website | CTO (T,O,F,Ky) | bar: 2020-04-01 to 2020-04-02
|  |  | 02. Requirements | Defining key components | CTO (T,F) | bar: 2020-04-02 to 2020-04-03
|  |  |  | Defining project requirements | Project Manager (K,T) | bar: 2020-04-04
|  |  |  | Defining system musts | CTO(T,F,Ky,O) | bar: 2020-04-02 to 2020-04-03
|  |  |  | Creating use cases/interviews | Digital Marketer(G,Ky) | bar: 2020-04-02 to 2020-04-05
|  |  |  | Produce functional specifications | CTO(T,F,Ky,O) | bar: 2020-04-05; 2020-04-08
|  |  |  | End-user research | Digital Marketer(G,Ky) | bar: 2020-04-02 to 2020-04-05
|  |  | 03. Design system | Technical specification (UML, databases, infrastructure) | CTO(K,N) | bar: 2020-04-08 to 2020-04-09
|  |  |  | Meeting regarding specifications | Everyone | 2020-04-10: Everyone
|  |  |  | Style tile | Designer(Ky,F) | bar: 2020-04-08 to 2020-04-11
|  |  |  | Wireframes/prototypes | Designer(Ky,F) | bar: 2020-04-09 to 2020-04-11
|  |  |  | New product photos | Digital Marketer(G) | bar: 2020-04-08 to 2020-04-09
|  |  |  | Producing marketing material | Digital Marketer(G) | bar: 2020-04-10 to 2020-04-12
|  |  |  | Intellectual property of prouced and future requirements/produced code | Copywriter(N) | bar: 2020-04-15 to 2020-04-19
|  |  | 04. Construction | Front-end coding (HTML, CSS, Javascript) | Front-End Dev(F,Ky) | bar: 2020-04-12; 2020-04-15 to 2020-04-19; 2020-04-22 to 2020-04-26
|  |  |  | Back-end coding (server side, logics) | CTO | bar: 2020-04-12; 2020-04-15 to 2020-04-19; 2020-04-22 to 2020-04-26
|  |  |  | SEO | Digital Marketer (G,F)
|  |  |  | Produce technical documentation | CTO/Front-end dev(T,F) | bar: 2020-04-15 to 2020-04-16
|  |  | 05. Implementation | Final testing and installation | Everyone | 2020-05-01: Everyone
|  |  |  | Website launch | Everyone | 2020-05-03: Everyone
|  |  | 06. Misc | Weekly testing | CTO(T,F,Ky) | bar: 2020-04-05; 2020-04-12; 2020-04-19; 2020-04-26
|  |  |  | Status meetings with stakeholders | Project Manager(K,O) | bar: 2020-04-05; 2020-04-12; 2020-04-19; 2020-04-26
|  |  |  | Morning stand-up meetings | CTO(T,F,K) | bar: 2020-04-01 to 2020-04-05; 2020-04-08 to 2020-04-12; 2020-04-15 to 2020-04-19; 2020-04-22 to 2020-04-26; 2020-04-29 to 2020-05-02
|  |  |  | Project management | Project Manager | bar: 2020-04-01 to 2020-04-05; 2020-04-08 to 2020-04-12; 2020-04-15 to 2020-04-19; 2020-04-22 to 2020-04-26; 2020-04-29 to 2020-05-03